## Functional Testing Checklist
FUNCTIONAL TESTING CHECKLIST
Equipment/System:
The following activities should be checked and verified to document handover from construction to commissioning. Unsatisfactory items that are critical to performing testing safely must be corrected prior to handover. Unsatisfactory items that are not critical to performing testing must be documented in the handover punch list, and testing may commence.
Item | Yes | No | N/A | Initials | Date | Classification | Status
Construction complete according to the P&IDs as required to commence testing: concrete complete, piping installed, piping supports installed, equipment installed and powered, instruments installed and powered. Note architectural components or other features that do not impact startup do not have to be completed.
Leak and pressure testing completed satisfactorily for all piping systems. | [5 empty] | Type-A | Open
Leak testing completed satisfactorily for all water holding basins. | [5 empty] | Type-B | In-Progress
Utilities are properly connected to commence testing: | [5 empty] | Type-C | Closed
- Utility water | [5 empty] | Disputed
- Potable water
- Seal water
- Fire water
- Compressed air
- Natural Gas
HVAC system operable (only for facilities where HVAC is required for commissioning activities; T&B not required).
Temporary facilities are in place (if applicable) to recirculate test water.
Individual equipment manufacturers' O&M Manuals have been completed.
Alignment of equipmnet complete, (only if alignment not completed by vendors).
Safety devices and equipment are installed, fully functional, adjusted, and tested.
PLCs installed, wired, pulled, and terminated.
Third party electrical tests and adjustments have been completed.
Point to point checks have been satisfactorily completed from the equipment /device to the PLC.
Walkthrough with commissioning team has been completed.
Commissioning punch list items have been documented and are attached to this form.
If any of the above are marked "NO", provide explanation or comment and details of any agreed action:
Attachments: (List any attachments to document above items)
Comments:
Verified by Vendor and Contractor: | Name:
Date: | Signature:
Approved by Construction Manager: | Name:
Date: | Signature:
Note on E8: Choose from the drop down list
Note on H8: Choose from the drop down list.
Note on I8: Choose from the drop down list.