## Functional Testing Checklist
OPERATIONAL READINESS CHECKLIST
The following deliverables should be completed during the commissioning phase of the project, prior to handover of the new systems to the operating team, in order that the system operators are fully prepared to take over and operate the new facilities.
Item | Yes | No | N/A | Classification | Status
DOCUMENTATION
O&M Manuals |  |  |  | Type-B | In-Progress
Red Line/As-Built Drawings
Construction Turnover Package (Quality Reports)
Commissioning Turnover Package (Test Reports/Settings)
Document Archive and Retreival System
SITE OPERATING PERSONNEL AND SUPPORT
Staffing Plan
Transportation and Accommodation
Maintenance Contracts
IT Operational Support
OPERATING PROCESS & PROCEDURES
Plant Description Document
Protection Coordination Studies
System Operating Studies
Performance Guarantee Monitoring Procedures
Control System Updates and Revisions
Data Transfer Systems
Communication Procedures and Decision Making Processes
Energy Isolation Procedures - LOTO
SAFETY/ENVIRONMENT/SECURITY
Emergency Response Plans
Spill Response Plans
Environmental Compliance Certificates
Safety Compliance
Access Management Plan
TRAINING
Central System Operator Training Plan
Local Operator Training Plan
Contractor/Vendor Provided Training
Owner Provided Training
REGULATORY & OTHER COMPLIANCE
Cyber/NERC Compliance - Initial Startup
Cyber/NERC Compliance - Ongoing Compliance
Software Maintenance Plan
DATA SYSTEMS
Performance Guarantee Monitoring
ASSET MANAGEMENT IMPLEMENTATION
Warranty Requirements
Spares Inventory and Maintenance
Preventative Maintenance Program
Asset Management Software System
Obsolescence Strategy
Data Backup Plan
EQUIPMENT/MATERIALS
First Fill Requirements
Special Tools/Equipment
Plant Furniture/Appliances
COMMISSIONING
Transfer of Care, Custody, Control
Type-A/B/C Deficiency Classification Process
Decision Making Processes
Performance Verification - Trial Period - Operating Plan